SOLUTION DESIGN TRACK

IBM AI Appliance: Program Plan - Draft

A proposed path from the initial configuration, available only by approved IBM RPQ, to a lab-proven, demonstrable, deliverable appliance

| Document ID | SD-2026-038 (provisional) |
| --- | --- |
| Version | 0.31 |
| Date | September 7, 2026 |
| Status | Working draft |
| Prepared for | IBM Engineering |
| Prepared by | Li9 Technology Solutions |
| Audience | IBM and Li9 only |
| Related | SP-2026-023, the IBM AI Appliance presentation, r29; SD-2026-029, the reference sources |

Purpose. This is Li9's proposed plan for moving the IBM AI Appliance from design to a deliverable solution, offered for IBM's review. It is built from published IBM, NVIDIA and Red Hat documentation and from read-only oc and nv data collection scripts run against the IBM Customer Demo Lab.

Next step. Confirm the architecture on a Fusion HCI with GPU nodes, H200 NVL preferred, and an SSS6000 connected directly to the Fusion HCI 200GbE top-of-rack switches, with Fusion HCI and the related IBM storage software at the current or next release. Global Data Platform remote mount on a hosted cluster is an IBM feature at that level; the RoCEv2 path is what the confirmation establishes.

Position. Customers are shown the appliance now. It is available only through an approved IBM request for price quotation (RPQ), not from the standard catalog; each RPQ is a configuration from the range in 1.3, not a custom build. The sequence to an RPQ-orderable product is proposed for IBM to establish and manage, with Li9 support as needed; when any configuration can be ordered is IBM's decision.

Why now. IBM's on-premises AI proposition needs two things this plan serves: an integrated appliance, and pricing customers can put into 2027 budgets, which are being set now. Pricing can be produced today by configuring Fusion HCI, the SSS6000, Red Hat subscriptions and services individually and presenting the total as one turnkey solution. Li9 has tools that do this from current price books.

Contents

1  The appliance being built	2

1.1  A self-contained solution	2

1.2  Support status of the design	2

1.3  The configuration range	3

1.4  Clusters and GPU allocation	4

1.5  Storage allocation for the AI workload	5

1.6  The value propositions the plan has to make true	6

2  Workstreams	8

WS1  Offering and orderability	8

WS2  IBM Customer Demo Lab platform build	9

WS3  GPU data path verification	10

WS4  Demonstrations and short pilots	10

WS5  Platform operations proof	11

WS6  Factory integrate, configure and test	12

WS7  Documentation, evidence and collateral	12

WS8  IBM confirmations	13

3  Proposed sequence	15

4  Proposed roles	17

5  Risks	18

6  What customers hear now, and what waits for proof	19

6.1  Stated now	19

6.2  Stated after demo lab proof	19

7  Outstanding Questions	20

8  Conventions	21

9  Reference sources	22

# 1  The appliance being built

One 42U rack of IBM compute and IBM storage: IBM Fusion HCI with Lenovo 9155-G04 GPU nodes carrying NVIDIA H200 NVL, attached over a 200GbE fabric to an IBM Storage Scale System 6000. Li9 can provide architecture, implementation and ongoing customer services as IBM Consulting or IBM Technology Expert Labs, across every area of an implementation and continuing under the services a customer purchases.

Three configurations define the range: Entry Level, Mid-Level, which adds a third GPU node and storage, and Maximum Configuration, the in-place growth path. Configurations between them are orderable, and more than one appliance can be ordered at once. Entry, Mid and Max refer to the three below.

## 1.1  A self-contained solution

The appliance is a self-contained AI solution, operated like a private cloud on site. It touches the customer environment only through the two network uplinks, identity and access control, the customer's databases and retrieval sources, SIEM forwarding and backup destinations.

In scope: integration with customer process and services, change approval, single sign-on and role-based access, databases, logging, backup. Out of scope: integration of the appliance infrastructure into customer infrastructure.

For initial implementations this is a fixed boundary, held so that problems specific to one or a few customers do not enter the platform. Changes that benefit every appliance are incorporated as soon as they are proven. The boundary is revisited once the infrastructure has stabilized.

The architecture is not tied to the components in the initial configurations. Future GPU generations, network switches, adapters, drives and software from IBM and its partners are supported by the IBM AI Appliance as IBM qualifies them, without a change to the architecture or design [FH1 p.32] [FH1 p.38].

## 1.2  Support status of the design

Design elements have different standing: IBM-documented as shipped, NVIDIA or Red Hat documented, supported per IBM but to be verified in writing, or Li9 proposed from supported components. The table gives each element's status and what makes it IBM-supported. The presentation states the design as delivered, by decision; this table stands behind it.

| Element | Status | What makes it IBM-supported |
| --- | --- | --- |
| Global Data Platform remote mount on a bare metal hosted cluster | IBM documented | Supported as shipped at Fusion HCI 2.13.0 [FH1 p.773] |
| Two hosted clusters, Test on virtual workers and Production on bare metal | IBM documented | Both hosted cluster forms are supported [FH1 p.743] |
| GPU nodes as bare metal node pools on a hosted cluster | Supported. Verify with IBM | IBM has stated it is supported; the published statement and the OpenShift release it applies from are pending (Q6). Red Hat lists the virtualized form as Technology Preview |
| RoCE enablement on the Storage Scale System | IBM documented | Documented procedure at 7.0.1 [DG1 p.31 to p.40] |
| RDMA on the CNSA cluster; Network Operator on OpenShift | IBM documented for CNSA | Documented for CNSA in general [CN1 6.0.0 p.22 to p.26]; whether the Fusion-created CNSA cluster accepts the parameters and which Network Operator level Fusion ships are pending (Q1, Q2) |
| GDS and GPUDirect RDMA on OpenShift | NVIDIA documented | Supported on OpenShift 4.18 and higher [GO1]; IBM's support position for Storage Scale as the filesystem is pending (Q1) |
| Lossless RoCEv2 configuration of the SN3700 pair under Fusion HCI switch management | Li9 proposed | Not described in the Fusion HCI documentation set; IBM Engineering confirmation of the switch configuration under Fusion management (Q11). This, with the two rows above, is what makes the end-to-end RoCEv2 path an IBM-supported configuration |
| One GPU node per node pool; per-pool changes | Red Hat documented | Node pools are updated individually [RH3]; whether the Fusion bundled update stages by pool is pending (Q4) |
| Test namespace by quota and MIG inside Production | Red Hat and NVIDIA documented | Standard OpenShift and GPU Operator function |
| NVLink two-way and four-way on the 9155-G04 | NVIDIA documented at the GPU | H200 NVL supports NVL2 and NVL4 [NV4]; orderability and support on the G04 is pending (Q5) |
| Three configurations; eight-port attach; third GPU node at Mid | Li9 proposed | IBM review and approval of rack units, environmentals and switch ports per configuration (Q8) |
| KV cache tier on the array read over GDS | IBM measured elsewhere | Published by IBM on another platform [RB4]; not published for this appliance; the demo lab measurement in WS3 |
| Storage allocation, filesets, placement policy | IBM documented | Standard Storage Scale function; the allocation is Li9's design |
| Factory integrate, configure and test | Li9 proposed | IBM Engineering and IBM Technology Expert Labs agreement on scope (Q9) |
| Delivered bandwidth figures | Li9 arithmetic | Measured by IBM Engineering on the appliance; marked [INF] until then |

## 1.3  The configuration range

| Component | Entry Level | Mid-Level | Maximum Configuration |
| --- | --- | --- | --- |
| GPU nodes, 9155-G04 | 2 | 3 | 4 |
| H200 NVL per node / total | 4 / 8 | 4 / 12 | 8 / 32 |
| GPU memory total | 1.1 TB [NV1] | 1.7 TB [NV1] | 4.5 TB [NV1] |
| Control / worker nodes, 9155-C14 | 3 / 3, 64 cores, 1024GB [FH1 p.37] |  |  |
| SSS6000 TLC | 24 x 7.68 TB, 147 TB usable; grows to 48 drives | 24 x 30.72 TB, 590 TB usable; grows to 48 drives | 48 x 30.72 TB, 1.18PB usable |
| QLC expansion shelf, 5149-F26 | Optional, 2.56PB usable | 12 x 122.88 TB, 1.18PB usable; grows to 26 drives | 26 x 122.88 TB, 2.56PB usable |
| SSS6000 attach | 8 x 200GbE | 8 x 200GbE | 8 x 200GbE |
| Delivered read, estimate | approx 85GB/s, set by the two GPU nodes [INF] | approx 130GB/s, set by the three GPU nodes [INF] | approx 170GB/s [INF] |
| Delivered write | 155GB/s, array limit [PP1] |  |  |
| Largest single model footprint | 564GB, four-way bridge [NV4] [NV1] |  |  |
| Software | - IBM Fusion HCI 2.13.x, or 2.14 once generally available - Red Hat OpenShift Platform Plus on the worker and GPU nodes [FH1 p.133] - Red Hat AI Accelerator subscription, one per GPU, in addition to the node subscription [RH1] - Ansible Automation Platform, one 100-node subscription - watsonx stack; Content-Aware Storage - NVIDIA AI Enterprise bundled with each GPU [FH1 p.135] [NV1] |  |  |
| Architecture and implementation | - Hub cluster plus two hosted OpenShift clusters by default, Test and Production; GPU nodes as bare metal node pools in Production, one node per pool - Two storage planes: Fusion Data Foundation from the hub provider; Global Data Platform remote mount to the SSS6000 through CNSA [FH1 p.773] - RoCEv2 fabric with GDS on the GPU path, a proposed composition of IBM-supported and NVIDIA-supported components; support status in 1.2 - Automated promotion of infrastructure and application changes from Test to Production - Factory integrate, configure and test; architecture, implementation and ongoing customer services by Li9 as IBM Consulting or IBM Technology Expert Labs |  |  |
| Support | - IBM hardware at Premium, 24x7 with proactive monitoring - Software at standard |  |  |

The three configurations share the same control and worker nodes, eight-port array attach, fabric and software, so they are designed, configured and supported the same way. Similarity gives way only where it adds cost or a disadvantage.

Mid differs from Entry in three components: a third GPU node with four cards, 30.72 TB TLC drives, and twelve QLC drives. The rack has the 3U slot and the two 200GbE ports the third node uses, so the attach and port map do not change. The third node was chosen over adding cards for availability: Production keeps two nodes through a node failure, and a test window on one node leaves two serving. Other configurations vary the same components, for example Entry GPUs with 48 x 7.68 TB TLC and the full QLC shelf for a data lakehouse. Software options are offered only where they will see wide use.

Physical layout and levels. No configuration is final until IBM has reviewed and approved its rack units, environmentals and switch ports, the eight array ports, the GPU node ports and the SSS6000 utility node included. IBM Engineering settles the rack layout and the software and microcode levels for each configuration during initial engineering. That work does not gate customer presentations, which describe the range; an order fixes layout and levels when IBM approves it.

Version. 2.13.x is the level of record; its currency includes OpenShift 4.21 [FH1 p.32]. 2.14 is expected to be generally available in October or November 2026 and is offered to customers from that point. Customers do not receive pre-release code; an early release that is part of IBM's published release schedule is treated as released.

## 1.4  Clusters and GPU allocation

A GPU node belongs to one hosted cluster's node pool [RH3], and MIG divides a card only within its node. GPU capacity is therefore dedicated to the cluster that holds the node; moving it between clusters means moving a node, a drain and reprovision measured in tens of minutes. The default layout follows from that.

- Two hosted clusters by default. Test, for promoting platform and application changes; Production, holding every GPU node. Test's workers are virtual machines on the hub cluster's worker nodes through OpenShift Virtualization, so Test costs no rack space; a virtualized hosted cluster has no Storage Scale remote mount [FH1 p.773] and uses the Ceph plane, which is all Test needs. A bare metal Test cluster, with its own servers and a direct array mount, is a purchased option. Promotion runs Test to Production through an approval step, automated with Ansible Automation Platform.

- One GPU node per node pool in Production. Each node pool carries its own version and configuration [RH3], and the GPU Operator can carry a driver level per node [GO1]. An infrastructure change is applied to one pool, the node is drained and reprovisioned, test workloads run against it, and the change then rolls to the next pool. A node can equally be drained and configured for any non-production purpose and returned. No node is dedicated to non-production.

- A Test namespace inside Production. One card per node is reserved for model and agent testing by resource quota, with MIG on that card where smaller instances are wanted. At Entry that is six cards serving and two testing; at Mid, nine and three; at Max, twenty-eight and four. Moving capacity between the two is a quota change.

- Sizing rule. Production is sized for N minus one nodes during any test window. At Entry a test window runs on four cards; at Mid, on eight across two nodes; at Max, on twenty-four. At Mid and Max, Production still survives a second node failure during the window.

- When a node moves to the Test cluster instead. A change to the hosted control plane itself, the API server and etcd, is cluster-wide and cannot be staged by node pool. For that, and for customers whose change control requires that Production be untouched by test activity, a GPU node is scaled out of its Production pool into a node pool on the Test cluster, configured there, and scaled back. The Test cluster has its own fileset on the array from the start for this reason.

- Other layouts. A GPU-equipped Test cluster at Max, a QA cluster, a sandbox, or more, are best-practice options architected for a specific customer's requirements. They are not part of the default and are not presented as such.

One item to confirm with IBM. Red Hat updates node pools individually, each on its own OpenShift version after the hosted control plane [RH3 Updating hosted control planes], and NVIDIA applies driver levels per node [GO1], so the per-pool canary is a platform capability. Whether the Fusion HCI bundled update, firmware, OpenShift and Fusion together, exposes that staging for hosted clusters or drives every node pool in one pass is IBM's to say (Q4). Operator and driver canaries stand either way.

## 1.5  Storage allocation for the AI workload

Storage is allocated by access pattern; the patterns are inference, retrieval and agents. The presentation carries the rules in its slide notes; this section is the detail.

Two planes, two jobs. The Ceph plane on the hub worker nodes holds platform data: hosted cluster state and images, application PVCs, VM disks, automation state, and the CAS local cache on native RBD [FH1 p.29]. The SSS6000 holds the AI data: model weights, the KV cache tier, the retrieval data set and the lakehouse, reached through CNSA over RoCEv2 with GDS from GPU nodes and over TCP from standard workers. Nothing an inference pod reads at volume lives on Ceph, which has no GDS path. GPU node NVMe is scratch [FH1 p.38].

| Fileset | Pool | What it holds and how it is read | Placement and sizing rule |
| --- | --- | --- | --- |
| weights | TLC | - Model weights for the models in use, 141GB to 564GB each at FP8 - Read at load and swap over GDS; large sequential; persistent | - Quota for the models in use plus one - Never migrated |
| kvcache | TLC | - The KV cache tier for the serving engine - Written and read constantly by GPU pods; small, scattered; ephemeral | - Pinned to TLC by placement policy; a cache read from QLC loses to recompute - Sized at about 40GB per long-context session to be kept warm; the deliberate sizing decision at Entry |
| retrieval | TLC, migrating to QLC | - The indexed documents and their vectors that CAS writes and the agents search - Ingest over TCP from standard workers; then small reads | - Hot on TLC; migrated to QLC by age; pulled back on access - At Mid and Max the whole set stays on TLC |
| lakehouse | QLC | - Raw documents before ingest, cold retrieval data, datasets parked for later | - QLC only; optional at Entry, present at Mid and Max |
| test | TLC | - The Test namespace's working set inside Production | - Separate fileset so a test cannot touch the Production cache |
| per cluster | TLC | - One fileset per hosted cluster that mounts the array, Production by default | - Test cluster uses Ceph only and has no mount [FH1 p.773]; NFS or object share over TCP where a Test workload needs the data |
| Ceph plane | hub NVMe | - Platform data as listed above; CAS local cache on RBD [FH1 p.29] | - Approx 30TB in every configuration; does not grow with GPU count |
| GPU scratch | node NVMe | - Staging while weights load; a local cache tier under Dynamo if chosen | - Ephemeral; nothing persistent; gone on reprovision |

Writes. Ingest, CAS indexing and document loads, is the sustained write and fits inside the 155GB/s array limit [PP1]. Checkpoints are the burst write and exist only where fine tuning is in scope; the default sizing assumes adapter tuning, and full fine tuning is a customer-specific option with its own sizing. Training from scratch is not a use case.

By configuration.

- Entry: 147 TB TLC holds weights, the cache tier and the hot retrieval set; the cache quota is the one to set deliberately. The QLC shelf makes a lakehouse possible.

- Mid: 590 TB TLC sizes the cache for reuse across many sessions and keeps the whole retrieval set hot; 1.18PB QLC is the lakehouse; three GPU nodes read it.

- Max: 1.18PB TLC leaves the placement policy managing capacity rather than protecting the cache; 2.56PB QLC is lakehouse and archive.

The best-practice storage configuration document, a WS1 deliverable, carries the quotas per configuration.

## 1.6  The value propositions the plan has to make true

Each proposition from the presentation is listed with what has to be true for it to hold, and where in this plan it gets proven. Nothing on the left is presented to a customer as proven until the right-hand column is done.

| Proposition | What must be true | Proven in |
| --- | --- | --- |
| A self-contained solution operated like a private cloud on site | - The appliance touches the customer only through the uplinks, identity, databases and retrieval sources, SIEM and backup destinations - Every demonstration integrates through those interfaces and no others | WS4, WS5 |
| One rack, integrated and tested together, IBM compute and IBM storage under IBM support | - Orderable as one IBM order, initially only by approved IBM RPQ, with a name IBM stands behind - The factory method exists and produces a report per serial number | WS1, WS6 |
| One platform for AI, containers and VMs, with Test and Production as separate clusters | - Two hosted clusters on one hub; GPU nodes as bare metal node pools in Production - VMs run alongside - Changes promote from Test to Production by automation | WS2, WS5 |
| GPU and storage are pools; the split changes without a rebuild | - MIG layouts and NVLink combining work on the G04 as documented - Within Production, capacity moves by quota; between clusters, by node pool - Storage Scale namespace with two tiers and policy placement | WS3, WS5 |
| Agentic AI with retrieval grounded in enterprise content and governance built in | - watsonx Orchestrate, CAS and governance run on the demo lab - Questions are answered over controlled content with inherited permissions | WS4 |
| GPUs usable on day one: enable, allocate, observe | - GPU Operator on the Production cluster, MIG manager, telemetry in the shared stack | WS2, WS5 |
| One data path, one security model | - GDS path from the array into GPU memory works for a named workload - PVCs, backup, RBAC and compliance operate as described | WS3, WS5 |
| One operations stack, updates as one bundle, multicluster | - Single console, Call Home, bundled update exercised - Per-pool canary demonstrated - Hosted cluster lifecycle demonstrated | WS5 |
| Fast storage: model load in seconds, saved conversation state read back in about a second | - Measured model load and KV cache restore on the demo lab attach, then on the factory rack | WS3, WS4, WS6 |
| Bandwidth headroom against the NVIDIA guideline | - nsdperf and IOR on the demo lab attach - The 86 percent allowance replaced by a measurement | WS3, WS6 |
| Factory integrate, configure and test with a report per serial number | - Five layers plus layer zero defined, tooled, and rehearsed once end to end | WS6 |

# 2  Workstreams

Two labs. IBM Engineering tests and finalizes the appliance in its own lab. The IBM Customer Demo Lab, built by IBM lab engineers with Li9 support to the finalized configuration, serves demonstrations and pilots under two weeks; it is rebuilt by script into any configuration in the range and its build is documented as a customer deliverable. Longer pilots are not part of the initial sales effort.

Eight workstreams, proposed for IBM to establish and manage with Li9 support as needed: offering and documentation run throughout; four run in sequence through the demo lab; one is the factory method, which IBM executes and Li9 rehearses; one is the IBM confirmations track. No calendar dates; section 3 gives the order.

## WS1  Offering and orderability

Objective. Turn the configuration into something IBM can take an approved RPQ order for, with a name, a part list, an entitlement structure, a support structure and pricing inputs, and set the path from RPQ to a standard catalog offering. The date from which orders are taken is IBM's decision.

Work

- Fix Entry as the initial unit and freeze the part list from the configuration workbook against the IBM configurator; define the range between Entry and Max that is offered.

- Quote Red Hat OpenShift Platform Plus on the worker and GPU nodes; control plane nodes are not metered. Advanced Cluster Security, Quay and fleet policy come with it.

- Include Ansible Automation Platform with every appliance on one 100-node subscription. It is the vehicle for the scripted rebuild, the Test to Production promotion, the per-pool canary and the factory method.

- Assemble the entitlement and activation inventory into the order: Fusion HCI license metric and core count [FH1 p.860], Platform Plus subscriptions and AI Accelerator subscriptions per GPU [RH1], Ansible Automation Platform, NVIDIA AI Enterprise activation per GPU serial [FH1 p.135], Storage Expert Care Premium, standard software support.

- Obtain from IBM the RPQ route and the offering name, and IBM's review and approval of rack units, environmentals and switch ports for each configuration in the range.

- Agree with IBM the conditions under which the appliance moves from RPQ to a standard catalog offering, and the demo lab evidence that supports that move.

- Produce the pricing inputs and the services scope: architecture, implementation, the factory method and the on-site repeat, and ongoing customer services, provided by Li9 as IBM Consulting or IBM Technology Expert Labs. Planning basis for ongoing services in the initial offering: six months, one engineer part time.

- Produce the best-practice storage configurations for the Ceph plane and the SSS6000 at Entry, Mid and Max, for inference, retrieval and agentic workloads, as the reference the demo lab is built to and the RPQ package cites; the rules are carried in the notes of the presentation's configuration, data path and bandwidth slides, and the detail is section 1.5 of this plan.

- Set the claim set for customer conversations: what is stated before demo lab proof, what is stated after.

- Define how more than one appliance is ordered and delivered together.

| Depends on | - IBM confirmation of the RPQ route and the offering name - IBM review and approval of rack units, environmentals and switch ports per configuration - The entitlement structure of the IBM order - The Fusion license metric applied to 64-core control nodes |
| --- | --- |
| Proposed owner | Li9 with IBM Offering Management. |
| Produces | - Order composition document - Entitlement and activation sequence - Pricing inputs and services scope - Best-practice storage configurations for Entry, Mid and Max - Claim set for customer conversations |
| Exit state | An IBM RPQ order can be placed for a configuration in the range with every subscription and activation accounted for. |

## WS2  IBM Customer Demo Lab platform build

Objective. Bring the IBM Customer Demo Lab to the level of record and build the platform structure of the appliance on it: hub cluster, the Test and Production hosted clusters with the GPU nodes as single-node pools in Production, Global Data Platform remote mount to the lab array, a lossless RoCEv2 fabric at both ends, and the promotion automation.

Work

- IBM updates the demo lab to 2.13.1, or 2.14 once available, on the corresponding OpenShift level. Rerun the cluster and node collections.

- Build the Test cluster with virtual machine workers on the hub worker nodes, and the Production cluster with the demo lab's two GPU nodes as one-node pools; the demo lab has two GPU nodes and demonstrates Entry directly and Mid and Max by script within that limit. Retire the virtualized hosted clusters currently on the GPU nodes.

- Create the Test namespace in Production with one card per node reserved by quota and a MIG layout on that card.

- Install Global Data Platform remote mount on Production from the hub by label, against the lab array, with a fileset per cluster. Read the resulting CNSA cluster resource to establish whether it carries or accepts the RDMA parameters.

- Enable RDMA on the CNSA cluster and on the array side, and enable GPUDirect Storage on both storage and client clusters.

- Build the lossless fabric on the SN3700 pair per the RoCEv2 and GDS design, and the matching host configuration. Confirm with the switch and host collections.

- Install the NVIDIA Network Operator at the level IBM ships, compare it with the 25.7.0 NVIDIA lists for OpenShift, and the GPU Operator at a supported level with the GDS driver image; record the levels.

- Add VLAN 3201 and the storage routing the remote mount prerequisites call for.

- Implement the promotion automation with Ansible Automation Platform: Test cluster to Production cluster for infrastructure and application changes with an approval step; Test namespace to Production namespace for models and agents.

- Implement the per-pool canary runbook: drain one GPU node pool, apply the change, verify from the Test namespace, roll to the next pool. Implement the node-move runbook to and from the Test cluster.

- Script the entire build so the demo lab can be rebuilt into any configuration in the range, and document it as the customer build document.

| Depends on | - The 2.13.1 or 2.14 update - The finalized configuration from IBM Engineering, which the demo lab is rebuilt to match - Li9 supports the IBM lab engineers on the build; Li9 hands-on access to the demo lab is requested with this plan - NVIDIA publishes GDS as supported on OpenShift 4.18 and higher, so the fabric build does not wait on a vendor answer |
| --- | --- |
| Proposed owner | IBM Customer Demo Lab engineers, supported by Li9. |
| Produces | - Cluster, node and switch collections at the new level - The CNSA cluster resource as created by Fusion - The fabric configuration as built - gdscheck output from a test pod - The promotion, canary and node-move runbooks - The rebuild scripts and the customer build document |
| Exit state | The demo lab runs hub plus Test and Production, Production mounts the lab array over RoCEv2 with GDS enabled at both ends, the runbooks work, and the whole build is scripted and documented. |

## WS3  GPU data path verification

Objective. Establish the storage-to-GPU path with measurements on the demo lab attach, in the order the value propositions depend on it, and hand the procedures to IBM Engineering for the factory method.

Work

- Bandwidth: nsdperf and IOR from the GPU nodes to the array over the lossless fabric. Replace the 86 percent allowance with a measured figure per node and aggregate.

- GDS: gdsio through the CNSA mount from a GPU pod; confirm the direct path is taken and not the compatibility path; record the stream API and checksum positions.

- Model load: time a 70B class and a 405B class weight load into GPU memory from the array, per node.

- KV cache: run vLLM or Dynamo with a tiered cache, tier on the remote-mounted filesystem, measure a 40GB class restore against a recompute of the same prefix.

- Latency and operation rate: small-block reads and metadata operations at realistic concurrency.

- Confirm the architecture on an SSS6000 connected directly to the 200GbE top-of-rack switches, wherever IBM provides one; the demo lab attaches an SSS3500, so until then it exercises the method and its figures are demo lab figures that do not transfer to the appliance.

| Depends on | - WS2 complete - The demo lab array |
| --- | --- |
| Proposed owner | IBM Customer Demo Lab engineers, supported by Li9; Li9 directly once access is granted. |
| Produces | - Measured tables for bandwidth, GDS, model load, KV cache restore and latency, each with the collection that produced it - A statement of what does and does not transfer to the SSS6000 - The procedures, handed to IBM Engineering |
| Exit state | The presentation's derived figures are replaced by measured demo lab figures with method, and the factory layer 3 and 4 tests have a rehearsed procedure. |

## WS4  Demonstrations and short pilots

Objective. Make the value propositions visible on the IBM Customer Demo Lab: agentic AI over governed content, a model loading in seconds, a saved conversation restored in about a second, the GPU pool re-partitioned by quota, a canary change on one GPU node pool, and a change promoted from Test to Production. Every demonstration integrates with the customer side through the interfaces in 1.1 and no others.

Work

- Deploy watsonx Orchestrate and watsonx.governance on Production; deploy Content-Aware Storage 1.1.5 with an NFS or filesystem data source of representative documents with mixed permissions.

- Activate NVIDIA AI Enterprise against the lab GPU serials and pull the NeMo Retriever microservices CAS uses through an NGC key.

- Build one agent that retrieves, reasons and acts over the indexed documents, and show that a user cannot surface a document they could not open.

- Script the storage demonstrations: cold model load timed; a long-context session saved and restored with the timing displayed; the same session recomputed for contrast.

- Script the GPU demonstrations: a quota move between the Test and Production namespaces; a MIG layout change on the Test card; a canary change on one node pool with the drain, verification and roll to the second pool shown.

- Script the operations demonstrations: telemetry for the GPU and array on one console, a Call Home event, a backup and restore of the agent application, a change promoted from Test to Production with the approval step.

- Script the customer-side integration demonstrations: single sign-on and role-based access from an external identity provider, a customer database as a retrieval source, SIEM forwarding, an external backup destination.

- Define the short pilot: under two weeks, on the demo lab, on a configuration from the range, with the customer's own documents and identity, and a rebuild to baseline afterwards.

- Record each demonstration and the pilot as a repeatable runbook so anyone from Li9 or IBM can run it without the author.

| Depends on | - WS2 and WS3 - The model licenses and the demonstration document set - Li9 hands-on access to the demo lab |
| --- | --- |
| Proposed owner | Li9, with the IBM Customer Demo Lab engineers. |
| Produces | - Runbooks for each demonstration and for the short pilot - A recorded walkthrough - The figures displayed live - The rebuild-to-baseline script |
| Exit state | A customer demonstration or a short pilot can be run on demand and the demo lab returned to baseline afterwards. |

## WS5  Platform operations proof

Objective. Exercise the operational claims so they are demonstrated, not described: single console, one bundled update, per-pool canary, backup and restore, compliance evidence, hosted cluster lifecycle.

Work

- Run one Fusion HCI bundled update on the demo lab and record the workload behavior during it; establish whether it can be staged by node pool.

- Run the per-pool canary for a GPU driver level change and record the capacity during the window.

- Configure Call Home and proactive monitoring and trigger a hardware event to show the path to IBM Support.

- Back up and restore the demonstration application with Fusion Backup and Restore; confirm what is and is not covered for hosted clusters.

- Run the Compliance Operator with CIS and NIST profiles and keep the reports as evidence.

- Promote an infrastructure change from Test to Production by automation, with an approval step.

- Confirm identity integration with an external provider and namespace-scoped access.

| Depends on | - WS2 |
| --- | --- |
| Proposed owner | IBM Customer Demo Lab engineers, supported by Li9. |
| Produces | - Update log - Canary log with capacity during the window - Call Home evidence - Backup and restore log - Compliance reports - Promotion log |
| Exit state | Every operations claim in the presentation has a demo lab artifact behind it. |

## WS6  Factory integrate, configure and test

Objective. Define the factory method IBM executes on every appliance. Li9 assists IBM in developing the OpenShift configuration and the automation the factory runs, rehearses the procedures on the demo lab, and works on customer implementations as IBM Consulting or IBM Technology Expert Labs.

Work

- Layer zero, entitlement and activation: the sequence from the IBM order number through OpenShift activation, Fusion entitlement key, pull secret, AI Accelerator subscriptions, NVIDIA AI Enterprise per serial, NGC key, Storage Expert Care and Call Home.

- Layer one, fabric and network: switch and host lossless configuration, nsdperf per port, MLAG state.

- Layer two, array delivery: IOR and metadata tests from the standard nodes.

- Layer three, GPU data path: gdscheck and gdsio per GPU node.

- Layer four, AI service claims: timed cache restore and model load per node.

- Layer five, platform health: IBM's own precheck tooling, Storage Scale health, DCGM diagnostics.

- Define the report format per serial number and the on-site repeat scope; agree both with IBM Engineering and IBM Technology Expert Labs.

- Build the automation in Ansible Automation Platform, which ships with every appliance, so the on-site repeat is the same automation the factory ran.

- Rehearse the whole method on the demo lab and correct it from what the rehearsal teaches; IBM Engineering executes it on the appliance in its own lab.

| Depends on | - WS3 procedures - WS1 entitlement sequence - IBM agreement on scope |
| --- | --- |
| Proposed owner | IBM Engineering and IBM Technology Expert Labs execute; Li9 supplies the procedures and the rehearsal. |
| Produces | - The factory method document - The report template - One completed report from the demo lab rehearsal - The automation |
| Exit state | IBM can execute the method on a customer rack and produce the report. |

## WS7  Documentation, evidence and collateral

Objective. Keep the reference sources, the design documents and the customer collateral current with what the demo lab proves, so that every claim a customer hears traces to a page or a measurement.

Work

- Reference sources: rows for every new source and lab collection, page anchors for every PDF in the repository.

- Design: the RoCEv2 and GDS design updated from the demo lab build; the environment document reissued at the new level; the best-practice storage configurations issued.

- Presentation: 21 slides at r29, with Entry, Mid and Max configuration slides and the storage allocation rules in the notes. The notes are the AE study guide, structured per slide as a timed talk track, what to know, technical detail, why it matters, likely questions, what not to say, and sources, with every marker linked to its source. Figures are replaced by measured figures as WS3 produces them; customer-facing slides are added.

- Customer build document for the demo lab, and the demonstration and pilot runbooks.

- Customer collateral: the demonstration narrative, the claim set, the order summary.

| Depends on | - Everything |
| --- | --- |
| Proposed owner | Li9. |
| Produces | - Current versions of all documents at each milestone |
| Exit state | No claim without a source; no source without a row. |

## WS8  IBM confirmations

Objective. Obtain in writing the answers that gate specific steps, in the order the steps need them.

Work

- IBM Engineering: which NVIDIA Network Operator level Fusion HCI 2.13.x ships, against the 25.7.0 NVIDIA lists for OpenShift [GO1]; and IBM's support position on GDS with Storage Scale on OpenShift, given that the operator-level statement names local NVMe and NFS [GO1] while Storage Scale is in the cuFile partner matrix [CUF3 5]. NVIDIA publishes GDS as supported on OpenShift 4.18 and higher [GO1], so nothing gates on NVIDIA.

- IBM Engineering: whether the Fusion-created CNSA cluster resource under remote mount accepts the RDMA parameters, or the demo lab answers it first; whether the SSS side ships with GDS enabled.

- IBM Engineering: NVLink bridges orderable and supported on the 9155-G04 with H200 NVL, and four-way at Entry.

- IBM Engineering: whether the SN3700 pair can be configured for lossless RoCEv2 under Fusion HCI switch management and whether IBM supports that configuration; with the CNSA RDMA parameters and the Network Operator level, this is what makes the end-to-end RoCEv2 path IBM-supported.

- IBM Engineering: whether the Fusion HCI bundled update exposes the per-node-pool staging that Red Hat provides for hosted clusters [RH3 Updating hosted control planes], or drives every node pool of a hosted cluster in one pass.

- IBM: the OpenShift release at which GPU node pools on hosted clusters left Technology Preview, and the first Fusion level carrying it, in writing.

- IBM: the 2.14 general availability date.

- IBM Engineering: the agreed rack layout for each configuration in the range, and the compatible software and microcode levels for each, from initial engineering. Needed for the RPQ package, not for customer presentations.

- IBM Offering Management: order composition, name, entitlement structure.

- IBM Engineering: review and approval of rack units, environmentals and switch ports for each configuration, including the eight array ports, the GPU node ports and the utility node.

- IBM Engineering and IBM Technology Expert Labs: factory method scope and the on-site repeat.

| Depends on | - The questions in section 7 |
| --- | --- |
| Proposed owner | Li9 asks; IBM Engineering, IBM Offering Management and the IBM lab team answer. |
| Produces | - Written answers filed with the reference sources |
| Exit state | Every item that gates a milestone is answered before that milestone. |

# 3  Proposed sequence

Figure 1. Milestone sequence.

One date. Customers are presented to now, from the week of September 7. Everything after is a sequence proposed for IBM to establish and manage, with Li9 support as needed; the date from which IBM takes RPQ orders, for which configurations, and the time IBM takes to approve each one, are IBM's to state.

|  | Milestone | What it means |
| --- | --- | --- |
| M0 | Presented to customers | - Presentation released to IBM; this plan submitted for approval; IBM asked for the 2.13.1 date - Li9 hands-on access to the demo lab requested with the plan |
| M1 | IBM Customer Demo Lab at 2.13.1 or 2.14 | - Update applied; cluster, node and switch collections rerun - Nothing GDS-related is meaningful before this |
| M2 | Test and Production clusters, remote mount | - Hub plus Test and Production; GPU nodes as one-node pools in Production; array mounted through CNSA; the cluster resource read - The first architectural proof, and the answer to the RDMA question |
| M3 | Lossless fabric and GDS verified | - RoCEv2 at both ends, gdsio taking the direct path, bandwidth measured - Derived figures start becoming measured figures |
| M4 | Demonstrations runnable | - Agentic stack over governed content; model load, cache restore, quota move, canary and promotion demonstrations runnable on demand - Scripted rebuild and customer build document complete |
| M5 | Factory method rehearsed | - All six layers rehearsed once on the demo lab with a report produced - Procedures handed to IBM Engineering |
| M6 | RPQ package | - Order composition, entitlements, support, pricing inputs and services scope complete - IBM confirmation of the RPQ route |
| M7 | First approved RPQ order | - A customer RPQ order for a configuration from the range, with the factory method and the demonstration behind it - On IBM's timing |

M6 does not depend on M2 to M5. The offering work in WS1 runs independently of the demo lab, so once IBM opens RPQ orders a customer can order on the strength of the IBM confirmations while demo lab work completes. Demo lab timing changes only which claims are made before delivery, which is what the WS1 claim set is for.

GDS on OpenShift NVIDIA publishes GDS as supported on Red Hat OpenShift 4.18 and higher, and GPUDirect RDMA on OpenShift 4.18 and higher with Network Operator 25.7.0 [GO1]. The lossless fabric is built on that basis. What remains for IBM is the Network Operator level Fusion HCI ships and IBM's stated support for GDS with Storage Scale on OpenShift; both are answered by M2 in the course of the demo lab work.

# 4  Proposed roles

| Who | Does |
| --- | --- |
| Li9 | - Owns the plan, the design and the documents - Supports every area of an appliance implementation, and continues under the ongoing services the customer purchases - Supports the IBM Customer Demo Lab engineers in building and operating the lab to the finalized configuration, and takes hands-on work once access is granted - Supports the IBM Engineering lab as needed - Assists IBM in developing the factory OpenShift configuration and automation - Supplies the test procedures; supports customer demonstrations and pilots as needed; presents to customers - Provides architecture, implementation and ongoing customer services as IBM Consulting or IBM Technology Expert Labs |
| IBM Engineering | - Tests and finalizes the appliance in its own lab, with Li9 support as needed - Answers the engineering questions in section 7 - Executes the factory method |
| IBM Customer Demo Lab engineers | - Build and operate the demo lab with Li9 support - The 2.13.1 or 2.14 update; the lab array attach - Li9 hands-on access requested on approval of this plan |
| IBM Offering Management | - Order composition, offering name, entitlement structure, pricing - The RPQ route; the 2.14 general availability date |
| IBM Consulting, IBM Technology Expert Labs | - The organizations Li9 provides customer services as - Factory method scope and the on-site repeat |

# 5  Risks

| Risk | Consequence | Response |
| --- | --- | --- |
| Shipped Network Operator level below the 25.7.0 NVIDIA lists for OpenShift [GO1], or IBM's Storage Scale GDS support position narrower than assumed | GDS path works in the demo lab but is not supportable as shipped | - Record the level at M1 - Ask IBM for the support position in writing - NVIDIA's published support for GDS on OpenShift 4.18 and higher stands regardless |
| Fusion-created CNSA resource does not accept RDMA parameters | No GDS through remote mount on hosted clusters | - M2 answers it on the demo lab - Escalate to IBM Engineering with the resource in hand |
| NVLink bridges not orderable on the G04 | 564GB claim reverts; Entry limited to 141GB per model | - IBM confirmation in WS8 - Presentation carries the number by decision until then |
| Fusion bundled update applies to a hosted cluster as one unit | Per-pool canary limited to operator and driver changes; Fusion updates take Production as a whole | - Confirm with IBM in WS8 - State the update window in the claim set |
| 2.14 general availability slips past first orders | First deliveries on 2.13.x with an update to follow | - State 2.13.x as the level of record - Offer 2.14 from its general availability date only |
| IBM port review finds the switch port budget short for a configuration | That configuration waits on a port mapping revision | - Present the range; IBM approves each configuration before it is offered - Utility node ports counted in the budget from the start |
| Demo lab array is an SSS3500 | Numbers do not transfer to the SSS6000 | - Transfer the method - State every figure as a demo lab figure - IBM Engineering measures the appliance |
| Entitlement structure unclear | Order cannot be composed or priced | - Distribution and automation platform decided - Entitlement inventory with Offering Management first |
| Li9 hands-on access to the demo lab not granted after approval | Demo lab work proceeds only at the pace of IBM lab engineers; M2 to M5 stretch | - Li9 supplies scripts, procedures and documentation for IBM engineers to run - Access requested with the plan approval |
| A customer-specific change enters the platform | Problems specific to one customer; the self-contained boundary is lost | - Hold the boundary for initial implementations - Incorporate only changes that benefit every appliance |

# 6  What customers hear now, and what waits for proof

## 6.1  Stated now

- A self-contained AI solution, operated like a private cloud on site, that interfaces with the customer environment through the uplinks, identity, data sources, SIEM and backup destinations.

- One rack, IBM compute and IBM storage; Li9 can provide architecture, implementation and ongoing customer services as IBM Consulting or IBM Technology Expert Labs; hardware supported at IBM's highest tier with proactive monitoring.

- One platform for AI, containers and VMs, with Test and Production as separate clusters by default, governance built in and data staying on premises.

- GPU and storage as pools re-partitioned by policy; Entry, Mid and Max available only by approved IBM RPQ, each growing in place to the next, more than one appliance orderable at once.

- Agentic AI over the customer's own content with inherited access control.

- Every performance figure is an engineering estimate until measured on the customer's serial number, and the factory method is how it gets measured.

## 6.2  Stated after demo lab proof

- Measured bandwidth, model load and cache restore figures, as demo lab figures with method.

- The 564GB single-model footprint as IBM-confirmed rather than by decision.

- Max delivered bandwidth, once measured on four GPU nodes.

- The per-pool canary for Fusion-managed updates, once IBM confirms staging by node pool.

# 7  Outstanding Questions

The questions that gate milestones, in gate order.

|  | Question | Gates |
| --- | --- | --- |
| Q1 | Which NVIDIA Network Operator level does Fusion HCI 2.13.x ship, against the 25.7.0 NVIDIA lists for OpenShift [GO1], and what is IBM's support position on GDS with Storage Scale on OpenShift? | M2; the support statement in the RPQ package |
| Q2 | Does the Fusion-created CNSA cluster resource under remote mount carry or accept the RDMA parameters, and is GDS enabled on the SSS side? | M2 |
| Q3 | When is the demo lab updated to 2.13.1, when is 2.14 generally available, and from what date does IBM take RPQ orders for which configurations? | M1 and everything after; the level and timing of first deliveries |
| Q4 | Does the Fusion HCI bundled update expose the per-node-pool staging that hosted control planes provide [RH3], or does it drive every node pool of a hosted cluster in one pass? | The per-pool canary for Fusion updates; the claim set |
| Q5 | Are NVLink bridges orderable and supported on the 9155-G04 with H200 NVL, four-way at Entry? | The 564GB claim; M6 |
| Q6 | Which OpenShift release carries GPU node pools on hosted clusters out of Technology Preview, and which Fusion level first carries it? | Customer-facing support statement; M6 |
| Q7 | What does the IBM RPQ order carry: Platform Plus and Ansible Automation Platform quantities, Fusion metric and core count, SSS6000 entitlement, NVIDIA AI Enterprise activation? And what moves the appliance from RPQ to a standard offering? | M6 |
| Q8 | IBM review and approval of rack units, environmentals and switch ports for each configuration, with the utility node ports counted? | Every configuration; M6 |
| Q9 | What is the agreed factory method scope and on-site repeat? | M5 |
| Q10 | Which configurations between Entry and Max, and which software options, are offered at launch? | WS1; the demo lab rebuild set |
| Q11 | Can the SN3700 pair be configured for lossless RoCEv2, PFC, ECN and a RoCE traffic class, under Fusion HCI switch management, and does IBM support that configuration? | M3; the end-to-end RoCEv2 path as an IBM-supported configuration |

# 8  Conventions

- Tone: no rhetorical contrasts and no persuasive language. State what is done, what it produces and what it depends on. As a rule of thumb, if a sentence describes the parties rather than the work, or states something every reader already knows, it is removed.

- Scope: the appliance is self-contained. Integration with customer process and customer services is in scope; integration of appliance infrastructure into customer infrastructure is not, for initial implementations.

- One date: customers are presented to now. No other calendar dates are assigned; the sequence, and the date from which orders are taken, are IBM's to manage.

- Every figure is derived until measured; demo lab figures are demo lab figures; the factory report per serial number is the record.

- Hub cluster for the platform side, hosted cluster for the guest. Ethernet only; RoCEv2 is the RDMA transport of record.

- Factory process is integrate, configure and test, producing a factory test report. Not a certification.

- Reference sources per SD-2026-029, listed in section 9. The presentation is SP-2026-023.

# 9  Reference sources

Codes are as used in SD-2026-029. Page numbers are physical pages of the PDF held in the Li9 repository; section names are headings on the page. [INF] marks Li9 arithmetic or inference with no vendor source; [UNV] marks a vendor statement not yet published.

| Code | Source | Level / date | URL |
| --- | --- | --- | --- |
| FH1 | IBM Fusion HCI systems documentation set, 1,202 page PDF | 2.13.0; read September 3, 2026 | https://raw.githubusercontent.com/armandoariasli9/Doc/main/fusion-hci-systems-2.13.0-documentation-reduce-size.pdf#page=N |
| CN1 6.0.0 | IBM Storage Scale Container Native Storage Access PDF; substitute for 6.0.1, which has no PDF | 6.0.0; read September 5, 2026 | https://raw.githubusercontent.com/armandoariasli9/Doc/main/IBM-Storage-Scale-Container-Native-Storage-Access-6.0.0-20260731.pdf#page=N |
| GO1 | NVIDIA GPU Operator Platform Support | GPU Operator 26.7; page dated September 5, 2026 | https://docs.nvidia.com/datacenter/cloud-native/gpu-operator/latest/platform-support.html |
| CUF3 | NVIDIA GPUDirect Storage Release Notes; section 5 is the partner filesystem support matrix | v1.18; read September 3, 2026 | https://docs.nvidia.com/gpudirect-storage/release-notes/index.html |
| NV1 | NVIDIA H200 product page | Current | https://www.nvidia.com/en-us/data-center/h200/ |
| NV4 | NVIDIA Enterprise Reference Architecture, Appendix D | Current; read September 5, 2026 | https://docs.nvidia.com/enterprise-reference-architectures/white-paper/latest/appendix-d.html |
| PP1 | IBM Storage Scale System product page | Current | https://www.ibm.com/products/storage-scale-system |
| RH1 | Red Hat self-managed OpenShift subscription guide | January 23, 2026 | https://www.redhat.com/en/resources/self-managed-openshift-subscription-guide |
| RH3 | Red Hat OpenShift hosted control planes documentation; node pools belong to one hosted cluster | 4.20 | https://docs.redhat.com/en/documentation/openshift_container_platform/4.20/html-single/hosted_control_planes/index |